## Sheet1
SECTION | SUB SECTION | TOPIC | SUB TOPIC | HOURS | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
1 |  | Mechanical Design
| a |  | Structure Planning | 3
| b |  | Design Initiation | 8
| c |  | Design Detailing | 16
| d |  | Compartment Design(Electric systems) | 12
| e |  | Design Finishing | 16
| f |  | Design Documantation | 24
2 |  | Power Electronics
| a |  | Definite Power Calculations | 6
| b |  | Relevant Component Research | 5
| c |  | Vendor Contact | 5-6Days
| d |  | Circuit Modification for Compatibility | 4
| e |  | Parts on Order | 10Days
| f |  | Implement Modification | 8
3 |  | Control Electronics
| a |  | Plan Design and Services | 3
| b |  | Estimate Design Requirements | 2
| c |  | Research Similar Design Info | 8
| d |  | Finalize Circuit and Components | 4
| e |  | Propose Possible Simulation | 8
| f |  | PCB Design Initialization | 4
| g |  | PCB Design Improvements | 10
| h |  | PCB Finishing | 2
| i |  | Casing 3D Design | 5
| j |  | PCB Manufaturing Order | 10Days
4 |  | Manufacturing
| a |  | Tendor Acceptance | 3-5 Days
| b |  | Parts manufaturing | 3-4 Days
| c |  | 3D Print | 2 Days
5 |  | Assembly & Testing
| a |  | Electrical Part Testing | 12
| b |  | Electric part fixing | 3
| c |  | Overall Fixing | 6
| d |  | Testing and Debuging | 2

## Sheet2
SECTION | SUB SECTION | TOPIC | SUB TOPIC | HOURS | Human Resource | Material | Cost HR | Cost Material | Role | Rate/hr | in month
1 |  | Mechanical Design | [6 empty] | SD | 42 | 10000
| a |  | Structure Planning | 3 | Solidworks Designer & Lead |  | 315 |  | PCD | 34 | 8000
| b |  | Design Initiation | 8 | Solidworks Designer |  | 42 |  | CCD | 25 | 6000
| c |  | Design Detailing | 16 | Solidworks Designer & Lead |  | 1680 |  | Lead | 63 | 15000
| d |  | Compartment Design(Electric systems) | 12 | Solidworks Designer¦ Power Electronic Consultant¦Control System Consultant |  |  |  | Labour | 500/day | 2000
| e |  | Design Finishing | 16 | Solidworks Designer & Lead |  | 1680
| f |  | Design Documantation | 24 | Solidworks Designer & Lead |  | 2520
TOTAL |  |  |  | 79 |  |  |  |  | Power Circuit Component
|  |  |  | 10 Days |  |  |  |  | Component | Rate
2 |  | Power Electronics | [6 empty] | 700VA Miceotek UPS | 3000
| a |  | Definite Power Calculations | 6 | Power Circuit Designer |  | 204 |  | Battery | 7000
| b |  | Relevant Component Research | 5 | Power Circuit Designer |  | 170 |  | Wire | 500
| c |  | Vendor Contact | 5-6Days | PCD & Lead |  |  |  |  | 10500
| d |  | Circuit Modification for Compatibility | 4 | PCD & SD & Lead |  | 556
| e |  | Parts on Order | 10Days | PCD & Lead | Power Circuit Components |  | 10500 | Control Circuit Parts
| f |  | Implement Modification | 8 | PCD |  | 272 |  | LCD | 100
|  |  |  | 18 Days |  |  |  |  | MCU | 150
3 |  | Control Electronics | [6 empty] | Small Comp | 100
| a |  | Plan Design and Services | 3 | Control Circuit Designer & Lead |  | 264 |  | Tools | 200
| b |  | Estimate Design Requirements | 2 | CCD & Lead |  | 176 |  | PCB Order | 250
| c |  | Research Similar Design Info | 8 | CCD |  | 200 |  | 3D Part | 500
| d |  | Finalize Circuit and Components | 4 | CCD & Lead |  | 352 |  |  | 1300
| e |  | Propose Possible Simulation | 8 | CCD |  | 200
| f |  | PCB Design Initialization | 4 | CCD |  | 100 |  | Mechanical Body
| g |  | PCB Design Improvements | 10 | CCD & PCD & Lead |  | 590 |  | Stainless Steel | 5760 | 180/kg | 2mX1mX3mm | 32kg
| h |  | PCB Finishing | 2 | CCD |  | 50 |  | Nut Bolts and others | 1000
| i |  | Casing 3D Design | 5 | CCD & SD |  | 335 |  |  | 6760
| j |  | PCB Manufaturing Order | 10Days | CCD & Lead | Control Parts |  | 800
|  |  |  | 18 Days |  |  |  |  | Electrical Parts
4 |  | Manufacturing | [6 empty] | UVC Lights | 8400 | 700/each | 1feet
| a |  | Tendor Acceptance | 3-5 Days | Lead & mediater |  |  |  | Holders | 720
| b |  | Parts manufaturing | 3-4 Days | labour | Steel¦Aluminium¦Holders | 2000 | 6760 | Kill Switch | 200
| c |  | 3D Print | 2 Days | order | Filler |  | 500 | Electromech Key Lock | 500
|  |  |  | 10 Days | [5 empty] | 9820
5 |  | Assembly & Testing
| a |  | Electrical Part Testing | 12 | Lead &CCD&PCD |  | 1464 |  | Raw Material + Labour |  | 30380
| b |  | Electric part fixing | 3 | CCD & PCD |  | 177
| c |  | Overall Fixing | 6 | Lead & CCD & PCD & SD | Misc Material | 984 | 9820 | Human Resource Cost |  | 14659
| d |  | Testing and Debuging | 2 | All |  | 328
3 Days
|  |  | Cummilative Working Days | 28 Days |  |  | 14659 | 28380
[5 empty] | Cumulative Budget |  | 43039